## Simple Business Risk Register
SIMPLE BUSINESS RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
CSS library doesn't support modals because of bootstrap | Key design feature will be unavailable on login screen | 3 | 4 | 12 | pass in the key word (important) for specific CSS | Front-end team | 1
Client may pivot to a mobile-first design | Aspects of the application will be unusable on small screens | 4 | 4 | 16 | consider future design on mobile | product owner/ front-end team | 2
data protection | exposing client data to public/hackers | 5 | 2 | 10 | use private variables / train the backend team | backend team | 3
traffic overload | webpage not loading because of traffic | 5 | 2 | 10 | have a big host service | product owner | 4
5

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.